## SIT Exhaustive
No. | Scenario ID | Modul / Area | Field Skenario | Tipe | Deskripsi | Prasyarat | Langkah | Expected | Priority | Status Uji | Hasil Aktual | Bukti Pengujian | QA | Tanggal Uji
1 | MV-03 | MAVEN | Outbound API Fee | Positive | GetActivitiesByGroup CSA returns mixed fee flags | - | GET https://mavendev.kalbenutritionals.web.id/api/v1/df/outbound/SubdistApi/GetActivitiesByGroup?groupName=CSA | CONSUMER OFFER fee=True; ADVERTISING fee=False | High | Pass | n=2 map={'ADVERTISING IN TV': (False, 0.0), 'CONSUMER OFFER': (True, 0.5)} | Lihat Evidence | Ageng | 17/10/2026
2 | CODE-01 | MAVEN | Response wrap | Positive | Outbound uses {message,data} envelope | - | Inspect JSON | Envelope present | High | Pass | keys=['message', 'data'] | Lihat Evidence | Ageng | 17/10/2026
3 | MV-01 | MAVEN | Mapping Index | Positive | Open Mapping Subdist | - | Login + navigate | Index load (not login redirect) | High | Pass | ok=True url=https://mavendev.kalbenutritionals.web.id/Account/ChooseRole?returnUrl=http%3A%2F%2Fmavendev.kalbenutritionals.web.id%2FDF%2FMappingSubdist | Lihat Evidence | Ageng | 17/10/2026
4 | W0b-STOP | MAVEN | UI stopper | Negative | Unhandled | - | - | Complete | Critical | Fail | Locator.count: Unexpected token "=" while parsing css selector "#btnExportMappedExcel, #btnRefreshClaims, text=Region". Did you mean to CSS.escape it? Traceback (most recent call last): File "D:\Work\Source\TestCase_Generator\Project\DevelopmentFund\SIT_Exhaustive\run_sit_exhaustive.py", line 704, in wave0b_maven_ui page.locator("#btnExportMappedExcel, #btnRefreshClaims, text=Region").count() > 0 ~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~~^^ File "C:\Users\Lenovo\AppData\Local\Python\pythoncore-3.14-64\Lib\site-packages\playwright\sync_api\_generated.py", line 16870, in count return mapping.from_maybe_impl(self._sync(self._impl_obj.count())) ~~~~~~~~~~^^^^^^^^^^^^^^^^^^^^^^^^ File "C:\Users\Lenovo\AppData\Local\Python\pythoncore-3.14-64\Lib\site-packages\playwright\_impl\_sync_base.py", line 115, in _sync return task.result() ~~~~~~~~~~~^^ File "C:\Users\Lenovo\AppData\Local\Python\pythoncore-3.14-64\Lib\site-packages\playwright\_impl\_locator.py", line 423, in count return await self._frame._query_count(self._selector) ^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^ File "C:\Users\Lenovo\AppData\Local\Python\pythoncore-3.14-64\Lib\site-packages\playwright\_impl\_frame.py", line 136, in _query_count return await self._channel.send("queryCount", None, {"selector": selector}) ^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^ File "C:\Users\Lenovo\AppData\Local\Python\pythoncore-3.14-64\Lib\site-packages\playwright\_impl\_connection.py", line 69, in send return await self._connection.wrap_api_call( ^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^ ...<3 lines>... ) ^ File "C:\Users\Lenovo\AppData\Local\Python\pythoncore-3.14-64\Lib\site-packages\playwright\_impl\_connection.py", line 559, in wrap_api_call raise rewrite_error(error, f"{parsed_st['apiName']}: {error}") from None playwright._impl._er | Lihat Evidence | Ageng | 17/10/2026
5 | MK-01a | KICAO | MKPP open | Positive | Open MKPPDF | - | Login Muslih → /Transaction/MKPPDF | Form load | High | Pass | opened | Lihat Evidence | Ageng | 17/10/2026
6 | MK-01 | KICAO | LOV Group CSA | Positive | Select CSA not first row | - | LOV Group → CSA | Group=CSA | High | Pass | group=CSA | Lihat Evidence | Ageng | 17/10/2026
7 | MK-02 | KICAO | Activity CONSUMER OFFER | Positive | Add activity fee_expected=True pct=0.5 | - | LOV supplier BANDUNG SELATAN + activity + 3 SKP | Row saved; fee columns reflect master | High | Pass | fee_row_snip={'text': '1\n\t\t\n\t\t\n\t\t\n\t\n\t\t\n%\n\t\t\n\t', 'html': '<td><div id="lblActivityNoValue"> 1 </div></td><td> <div class="input-group"> <div class="input-group-btn"> <button type="button" class="btn btn-danger btnLOVSupplier" id="btnLOVSupplier" onclick="p_btnLOVSupplier_ | Lihat Evidence | Ageng | 17/10/2026
8 | MK-08 | KICAO | Activity ADVERTISING IN TV | Positive | Add activity fee_expected=False pct=0.0 | - | LOV supplier JAKARTA SELATAN + activity + 3 SKP | Row saved; fee columns reflect master | High | Pass | fee_row_snip={'text': '2\n\t\t\n\t\t\n\t\t\n\t\n\t\t\n\t\n\t\n\t', 'html': '<td><div id="lblActivityNoValue"> 2 </div></td><td> <div class="input-group"> <div class="input-group-btn"> <button type="button" class="btn btn-danger btnLOVSupplier" id="btnLOVSupplier" onclick="p_btnLOVSupplier_C | Lihat Evidence | Ageng | 17/10/2026
9 | W1-STOP | KICAO | Wave1 stopper | Negative | Unhandled | - | - | Complete wave | Critical | Fail | Locator.count: SyntaxError: Failed to execute 'evaluate' on 'Document': The string 'ancestor::div[contains(@class,'form-group') or contains(@class,'col-')][1]//a[contains(.,'Open Text Editor')], button[contains(.,'Open Text Editor')]' is not a valid XPath expression. at Object.queryAll (<anonymous>:6147:25) at InjectedScript._queryEngineAll (<anonymous>:6847:49) at InjectedScript.querySelectorAll (<anonymous>:6834:30) at eval (eval at evaluate (:290:30), <anonymous>:2:33) at UtilityScript.evaluate (<anonymous>:292:16) at UtilityScript.<anonymous> (<anonymous>:1:44) Traceback (most recent call last): File "D:\Work\Source\TestCase_Generator\Project\DevelopmentFund\SIT_Exhaustive\run_sit_exhaustive.py", line 395, in wave1_mkpp_happy ck = fill_ckeditors( page, ...<2 lines>... f"QA Ageng exhaustive {RUN_TAG}", ) File "D:\Work\Source\TestCase_Generator\Project\DevelopmentFund\SIT_Exhaustive\run_sit_exhaustive.py", line 100, in fill_ckeditors if btn.count() == 0: ~~~~~~~~~^^ File "C:\Users\Lenovo\AppData\Local\Python\pythoncore-3.14-64\Lib\site-packages\playwright\sync_api\_generated.py", line 16870, in count return mapping.from_maybe_impl(self._sync(self._impl_obj.count())) ~~~~~~~~~~^^^^^^^^^^^^^^^^^^^^^^^^ File "C:\Users\Lenovo\AppData\Local\Python\pythoncore-3.14-64\Lib\site-packages\playwright\_impl\_sync_base.py", line 115, in _sync return task.result() ~~~~~~~~~~~^^ File "C:\Users\Lenovo\AppData\Local\Python\pythoncore-3.14-64\Lib\site-packages\playwright\_impl\_locator.py", line 423, in count return await self._frame._query_count(self._selector) ^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^ File "C:\Users\Lenovo\AppData\Local\Python\pythoncore-3.14-64\Lib\site-packages\playwright\_impl\_frame.py", line 136, in _query_count return await self._channel.send("queryCount", None, {"selector": selector}) ^^^^^^^^^^ | Lihat Evidence | Ageng | 17/10/2026
10 | W2-SKIP | PRM | Skip | Positive | No MKPP from W1 | - | - | MKPP doc | High | Fail | STATE.mkpp_happy empty |  | Ageng | 17/10/2026
11 | W3-STOP | KICAO | Wave3 stopper | Negative | Unhandled | - | - | Complete | Critical | Fail | Locator.count: SyntaxError: Failed to execute 'evaluate' on 'Document': The string 'ancestor::div[contains(@class,'form-group') or contains(@class,'col-')][1]//a[contains(.,'Open Text Editor')], button[contains(.,'Open Text Editor')]' is not a valid XPath expression. at Object.queryAll (<anonymous>:6147:25) at InjectedScript._queryEngineAll (<anonymous>:6847:49) at InjectedScript.querySelectorAll (<anonymous>:6834:30) at eval (eval at evaluate (:290:30), <anonymous>:2:33) at UtilityScript.evaluate (<anonymous>:292:16) at UtilityScript.<anonymous> (<anonymous>:1:44) Traceback (most recent call last): File "D:\Work\Source\TestCase_Generator\Project\DevelopmentFund\SIT_Exhaustive\run_sit_exhaustive.py", line 608, in wave3_mkpp_reject ck = fill_ckeditors(page, f"SIT Reject {RUN_TAG}", "Reject T1 path", f"reject {RUN_TAG}") File "D:\Work\Source\TestCase_Generator\Project\DevelopmentFund\SIT_Exhaustive\run_sit_exhaustive.py", line 100, in fill_ckeditors if btn.count() == 0: ~~~~~~~~~^^ File "C:\Users\Lenovo\AppData\Local\Python\pythoncore-3.14-64\Lib\site-packages\playwright\sync_api\_generated.py", line 16870, in count return mapping.from_maybe_impl(self._sync(self._impl_obj.count())) ~~~~~~~~~~^^^^^^^^^^^^^^^^^^^^^^^^ File "C:\Users\Lenovo\AppData\Local\Python\pythoncore-3.14-64\Lib\site-packages\playwright\_impl\_sync_base.py", line 115, in _sync return task.result() ~~~~~~~~~~~^^ File "C:\Users\Lenovo\AppData\Local\Python\pythoncore-3.14-64\Lib\site-packages\playwright\_impl\_locator.py", line 423, in count return await self._frame._query_count(self._selector) ^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^ File "C:\Users\Lenovo\AppData\Local\Python\pythoncore-3.14-64\Lib\site-packages\playwright\_impl\_frame.py", line 136, in _query_count return await self._channel.send("queryCount", None, {"selector": selector}) ^^^^^^^^^^^^^^^^^^^^^^ | Lihat Evidence | Ageng | 17/10/2026